## transmission projects
TYNDP project number | Name of the project | Country/ies | TYNDP detailed project sheet [including project description and outcomes of the Cost Benefit Analysis] | Project website (as set by the promoter) | Current phase of the project [information as submitted by the promoter for the PCI process] | In your opinion, is a proposed project significantly contributing to market integration/sustainability/security of supply/competition and therefore needed from an EU energy policy perspective?
1 | RES in north of Portugal | PT | https://tyndp.entsoe.eu/tyndp2018/projects/projects/1 | https://www.ren.pt/en-GB/o_que_fazemos/projetos_interesse_2017/ | Investment V.Minho-R.Pena-Feira currently under Environmental Impact Assessment (30/12/2018) Investment Pedralva-Sobrado under Environmental Impact Studies development (30/03/2020)
4 | Interconnection Portugal-Spain | PT-ES | https://tyndp.entsoe.eu/tyndp2018/projects/projects/4 | https://www.ren.pt/en-GB/o_que_fazemos/projetos_interesse_2017/ https://www.ree.es/en/activities/grid-manager-and-transmission-agent/european-projects-common-interest-pci https://www.ree.es/es/actividades/gestor-de-la-red-y-transportista/proyectos-de-interes-comun-europeos-pic https://www.mincotur.gob.es/energia/planificacion/Planificacionelectricidadygas/desarrollo2015-2020/Paginas/desarrollo.aspx http://www.erse.pt/pt/consultaspublicas/consultas/Documents/64_1/PDIRT%202018-2027%20-%20junho%202017%20-%20Relat%C3%B3rio.pdf | Portugal: Section V.N.Famalicao-P. Lima Favorable EID, waiting for Permitting Portugal: Section P.Lima-Border under Environmental Impact Studies development (30/01/2019) Spain: The environmental process in Spain is waiting, to be completed, for the positive cross-border report of Portugal. This will allow the issuance of respective positive cross-border reports by respective environmental agencies in Spain and Portugal, as a mandatory previous step to finish de Environmental Permitting Process in each country. The expected date of obtaining environmental resolution in each country is June 2019 (30/06/2019)
16 | Biscay Gulf | FR-ES | https://tyndp.entsoe.eu/tyndp2018/projects/projects/16 | https://www.inelfe.eu/en/projects/bay-biscay | - Public-consultation procedure: Application of Public Declaration Utility in Spain and France (June 2019). The studies necessary for the preparation of the environmental impact study, in particular the fauna / flora inventories are ongoing. - Detailed engineering design: Detailed technical specifications (Nov 2018). Drafting of the detailed technical specifications for the cables and the converter stations works. - Tendering procedure: Procurement notice publication (Nov 2018) and tendering for contracts (April 2019). The procurement strategy is being drawn up for the publication of one or more European procurement notices
28 | Italy-Montenegro | ME-IT | https://tyndp.entsoe.eu/tyndp2018/projects/projects/28 | https://www.terna.it/en-gb/sistemaelettrico/pianodisviluppodellarete/progettidiinteressecomune.aspx | Currently the construction of the first HVDC module (600MW) is at a very advanced stage (commissioning foreseen by 2019), while the second HVDC module has been postponed and will be completed by 2026 (after the completion of the correlated projects in the Balkans and the development of the electricity markets in the area)
29 | Italy-Tunisia | TN-IT | https://tyndp.entsoe.eu/tyndp2018/projects/projects/29 | https://www.terna.it/en-gb/sistemaelettrico/pianodisviluppodellarete/progettidiinteressecomune.aspx | Completion of detailed feasibility studies and project design necessary to start the permitting procedure
31 | Italy-Switzerland | IT-CH | https://tyndp.entsoe.eu/tyndp2018/projects/projects/31 | https://www.terna.it/en-gb/sistemaelettrico/pianodisviluppodellarete/progettidiinteressecomune.aspx | Currently the permitting procedure is ongoing, and the project solutions are under review. The technical solution and the expected date for the authorization achievement will be updated accordingly.
35 | CZ Southwest-east corridor | DE-CZ | https://tyndp.entsoe.eu/tyndp2018/projects/projects/35 | https://www.ceps.cz/cs/projekty-spolecneho-zajmu | All three investment items in the project are in the high maturity project level: Investment item no. 313 OHL Kocin - Mirovka: land permit granting proces is on progress Investment item no. 315 OHL Kocin - Prestice: the documentation preparation for the land and construction permi granting process is on progress Investment item no. 311 substation Kocin: the construction phase is on progress
37 | Norway - Germany, NordLink | NO-DE | https://tyndp.entsoe.eu/tyndp2018/projects/projects/37 | http://www.statnett.no/Nettutvikling/NORDLINK/; https://www.tennet.eu/de/unser-netz/internationale-verbindungen/nordlink/ | Under construction. Both interconnector and converters.
47 | Westtirol - Vöhringen | DE-AT | https://tyndp.entsoe.eu/tyndp2018/projects/projects/47 | http://www.apg.at/de/netz/netzausbau/PCI/WesttirolZZ | Feasibility Study | Freier Warenverkehr ist ein Herzstück der Europäischen Union. Das gilt auch für Energie in jeder Form – im Energiebinnenmarkt muss Energie - im besonderen Strom - ungehindert über die nationalen Grenzen fließen können. Im größeren Markt ist Elektrzität á la longue billiger ist als im eng segmentierten Markt. Besser vernetzte Märkte bzw gemeinsame Preiszone bieten auch höhere Versorgungssicherheit. Der Ausbau grenzüberschreitender Netzinfrastruktur und die Verbindung der Marktgebiete ist somit von essentieller Bedeutung. Wir unterstützen deshalb die Durchführung der Machbarkeitsstudie zur Verstärkung der Leitung Westtirol – Zell/Ziller.
48 | New SK-HU intercon. - phase 1 | SK-HU | https://tyndp.entsoe.eu/tyndp2018/projects/projects/48 | On the Hungarian side: https://www.mavir.hu/web/mavir/pci-jeloltek On the Slovak side: https://www.mhsr.sk/energetika/medzinarodna-spolupraca/projekty-spolocneho-zaujmu-pci | On the Hungarian side; statutory procedure within permit granting process is ongoing. Issuance of the building permits are expected by 30/04/2019. On the Slovak side; public procurement for construction contractor has been launched. The contracts with selected construction contractors are expected to be signed by 30/06/2019.
62 | Estonia-Latvia 3rd IC | LV-EE | https://tyndp.entsoe.eu/tyndp2018/projects/projects/62 | http://www.ast.lv/en/transmission-network-projects/latvia-estonia-third-interconnection | The project is under construction
81 | North South Interconnector | NI-IE | https://tyndp.entsoe.eu/tyndp2018/projects/projects/81 | http://www.eirgridgroup.com/the-grid/projects/north-south/the-project/ | Interim phase between Permitting and Construction: In Ireland (IE) the comprehensive decision has been challenged in the courts and that judicial review process is expected to conclude in late 2018 or early 2019. In Northern Ireland (UK) the development planning consent has also been challenged in the courts and that judicial review process is not expected to conclude until at least September 2019. Advance procurement activities have commenced even though the legal challenges have not yet concluded. The NRAs in both jurisdictions have authorised the expenditure of up to €4m on the commencement of the procurement process for the major material and main contractor required for the construction phase. The contract for the design and testing of the overhead line steel towers is due to be awarded in late 2018 and the tender enquiry for the main construction contractor is due to issue in late 2018.
82 | RIDP I | NI-IE | https://tyndp.entsoe.eu/tyndp2018/projects/projects/82 | http://www.eirgridgroup.com/how-the-grid-works/ridp/ | Pre-application procedure.
96 | Keminmaa-Pyhänselkä | FI-SE | https://tyndp.entsoe.eu/tyndp2018/projects/projects/96 | https://www.fingrid.fi/en/grid/construction/cross-border-connections/third-interconnection-finland--sweden/ | The project is currently in Environmental Impact Assessment phase. Environmental Impact Assessment report of the overhead transmission line route Pyhänselkä-Keminmaa has been delivered to coordinating authority and authority has announced a public notice. The EIA phase will finish when coordinating authority gives statement on the EIA-report which is expected to be given in January 2019.
107 | Celtic Interconnector | IE-FR | https://tyndp.entsoe.eu/tyndp2018/projects/projects/107 | http://www.eirgridgroup.com/the-grid/projects/celtic-interconnector/the-project/ https://www.rte-france.com/en/project/celtic-interconnector-electrical-interconnector-between-france-and-ireland | Initial Design and Pre-Consultation
110 | Norway-Great Britain, North Sea Link | NO-GB | https://tyndp.entsoe.eu/tyndp2018/projects/projects/110 | http://northsealink.com/ | Construction phase
111 | 3rd AC Finland-Sweden north | SE-FI | https://tyndp.entsoe.eu/tyndp2018/projects/projects/111 | https://www.fingrid.fi/en/grid/construction/cross-border-connections/third-interconnection-finland--sweden/ | On the Swedish side Route studies and dialogue with authorities is on going and on the Finnish side the environmental impact Assessment is ongoing. The routing and environmental analysis phase will be finished in Sweden when the consultation underlay report is finished (expected end of 2019) and in Finland when the coordinating authority gives a statement on the EIA-report (expected March 2020).
120 | MOG II: connection of up to 2 GW additional offshore wind Belgium | BE | https://tyndp.entsoe.eu/tyndp2018/projects/projects/120 | http://www.elia.be/en/projects/grid-projects/MOG-II | There are currently 3 main project activities ongoing: (1) new zones for production and transmission of electricity in the Belgian part of the North Sea must be voted/officialised (action BE’s Government, MSP 2020-2026, target by the end of 2018 / beginning of 2019); (2) concepts voted end of August 2018 must be translated into law amendments (action BE’s Government, target by the end of 2018 / beginning of 2019); (3) Elia as Transmission System Operator performs the conceptual grid design study to deliver a proposal where to install platforms and lay cables in the identified zones in the MSP 2020-2026 (target: start by the end of 2018; end by the end of 2019 / beginning of 2020). A public consultation will most likely be held for the grid design proposal to ensure participation of wind farm developers and associations to the process
121 | Nautilus: 2nd interconnector Belgium - UK | GB-BE | https://tyndp.entsoe.eu/tyndp2018/projects/projects/121 | http://www.elia.be/en/projects/grid-projects/Nautilus | Feasibility phase
123 | LitPol Link Stage 2 | PL-LT | https://tyndp.entsoe.eu/tyndp2018/projects/projects/123 | https://www.pse.pl/obszary-dzialalnosci/inwestycje-infrastrukturalne/aktualnie-prowadzone-inwestycje | The project is in the implementation phase.
124 | NordBalt phase 2 | SE-LT | https://tyndp.entsoe.eu/tyndp2018/projects/projects/124 | https://www.svk.se/en/grid-development/grid-projects/ | Ekhyddan-Nybro/Hemsjö (733). Statutory procedure: end date (i.e. date of comprehensive decision): 10/01/2019
130 | HVDC SuedOstLink Wolmirstedt to area Isar | DE | https://tyndp.entsoe.eu/tyndp2018/projects/projects/130 | "http://www.50hertz.com/en/Grid-Extension/Onshore-projects/SuedOstLink; http://www.tennet.eu/de/unser-netz/onshore-projekte-deutschland/suedostlink" | Planned but not yet in permitting The § 6 NABEG application documents for the Federal Sectoral Planning for each of the sections A, B, C and D were submitted in 2017. The BNetzA held "application conferences” and defined the scopes of investigation for the sections A to D. Since then 50Hertz and TenneT are continually creating the application documents for the § 8 NABEG procedure. It is important to note that according to the TEN-E Regulation Article 10 (1), the project has not entered the status of “permitting” yet. Nonetheless, several activities with respect to planning and permitting (Federal Sectoral Planning) – which have to be conducted according to German Law before the permitting phase according to the TEN-E Regulation begins – have already been started and to some extent completed. Moreover a tender of major suppliers have been launched and contract awarding is planned for early 2020.
138 | Black Sea Corridor | RO-BG | https://tyndp.entsoe.eu/tyndp2018/projects/projects/138 | https://www.transelectrica.ro/web/tel/proiecte-de-interes-comun; http://www.eso.bg/fileObj.php?oid=1179 | Investment no: 273 – permitting - the expected commissioning year 2020 Investment no: 275 – permitting - the expected commissioning year 2022 Investment no: 800 – permitting - the expected commissioning year 2021 Investment no: 715 – permitting - the expected commissioning year 2021
142 | CSE4 | BG-GR | https://tyndp.entsoe.eu/tyndp2018/projects/projects/142 | ESO's website http://projects.eso.bg/projects/ and IPTO’s website: http://www.admie.gr/en/transmission-system/system-development/projects-of-common-interest/project/article/2194/ | Investment 258 - permitting - March 2019 Investment 262 - permitting - March 2019 Investment 257 - permitting - March 2019 Investment 256 - permitting - September 2019 on Bulgarian territory&November 2018 on Greek territory
144 | Mid Continental East corridor | RO-RS | https://tyndp.entsoe.eu/tyndp2018/projects/projects/144 | https://www.transelectrica.ro/web/tel/proiecte-de-interes-comun | The investment no: 269 “New 400 kV OHL between Portile de Fier and Resita” – under construction – the expected commissioning year is 2021 The investment no: 270 “Upgrading of existing 220 kV double circuit OHL Resita-Timisoara-Sacalaz-Arad to 400 kV double circuit” - the expected commissioning year is 2027 and the investment has been split in two sections: -“Internal line between Resita and Timisoara/Sacalaz” – permitting – the expected commissioning year is 2023 -“Internal line between Arad and Timisoara/Sacalaz” – planned but not yet in permitting - the expected commissioning year is 2027 The investment no: 701 “New 400 kV Resita substation” – the expected commissioning year is 2021 The investment no: 705 “Replacement of 220 kV substation Timisoara with 400 kV substation” – the expected commissioning year is 2023
150 | Italy-Slovenia | SI-IT | https://tyndp.entsoe.eu/tyndp2018/projects/projects/150 | https://www.terna.it/en-gb/sistemaelettrico/pianodisviluppodellarete/progettidiinteressecomune.aspx | On Italian side the permitting procedure is in progress, and in Slovenia a new pre-feasibility study is ongoing and expected to finish by the end of 2019. The completion of the authorization procedure on Italian side is expected by 2020 (the date below refers only to the Italian part of the project).
153 | France-Alderney-Britain | GB-FR | https://tyndp.entsoe.eu/tyndp2018/projects/projects/153 | www.fablink.net and http://www.rte-france.com/fr/projet/interconnexion-france-aurigny-grande-bretagne-fab | The current phase of the project is the permitting process which is expected to finish by mid-2019 (Déclaration d'utilité publique). In order to clarify and confirm regulatory treatment for the project, FAB Link has recently submitted an investment request on the basis of Article 12 of Regulation 347/2013. The next step is to progress to receive regulatory approvals and then to complete the procurement process and a financing process to lead to a final investment decision.
167 | Viking DKW-GB | GB-DK | https://tyndp.entsoe.eu/tyndp2018/projects/projects/167 | 'http://viking-link.com | The project is in the Permitting phase. This phase is expected to conclude with the granting of UK onshore and offshore consents by 9 April 2019.
170 | Baltics synchro with CE | PL-LT | https://tyndp.entsoe.eu/tyndp2018/projects/projects/170 | http://www.litgrid.eu/index.php/grid-development-/strategic-projects-/synchronous-operation-/137 | ENTSO-E RGCE Connection agreement and Catalogue of Measures under preparation. Expected completion March 2019 Internal reinforcements in the Baltic States (phase 1 investments) are in the preparation phase: construction planned 2020-2025.
172 | ElecLink | GB-FR | https://tyndp.entsoe.eu/tyndp2018/projects/projects/172 | www.eleclink.co.uk | Q42019
174 | Greenconnector | IT-CH | https://tyndp.entsoe.eu/tyndp2018/projects/projects/174 | www.greenconnector.it | Final approval by the authorities of the new site of the converter station and of the related variation of the cable route.
183 | DKW-DE, Westcoast | DK-DE | https://tyndp.entsoe.eu/tyndp2018/projects/projects/183 | 'www.klixbuell-endrup.eu | 'Pre-application Procedure started on 30 April 2018 German part: On 18 April 2018 public dialogue on West Coast project "Klixbüll (Niebüll) to Danish border" was launched. In cooperation with the Ministry for Energy Transition, Agriculture, Environment, Nature and Digitization as well as the association Deutsche Umwelthilfe, a proposal corridor will be developed within the framework of this dialogue process with all stakeholders concerned, on which the further route planning will be based. The results of the Citizens' and Technical Dialogue will be presented by the end of 2018 at a Conference. There are also other offers for dialogue. The submission of the planning approval document is scheduled for the year 2019. Danish part: Pre-application Procedure started in Denmark in the autumn 2017 and on the 7th of March, an application was sent to the municipalities about the project. They sent the application to the Environmental Agency which is authority for the EIA process. The first public hearing started 9th of April and ended 9th of May 2018. Investigations for the EIA report is ongoing and the EIA report will be sent to the Environmental Agency in Q3 2019. The second public hearing periode is in Q4 2019. The EIA permit is expected in Q1 2020.
190 | NorthConnect | NO-GB | https://tyndp.entsoe.eu/tyndp2018/projects/projects/190 | www.northconnect.no | In Permitting. Key achievements since Q2 2017: - Secured Grid Connection for Sima, Norway (Q2 2017) - Submitted license applications for the Norwegian side (Foreign Trade License and Construction License) (June 2017) - Cap&Floor process – IPA Ofgem decision (January 2018) - Marine Survey Norwegian-Scotland completed (January 2018) - Marine License application for UK submitted (June 2018) - Released Invitations to Tender for Cable and Converter Contracts (Q3/Q4 2018) NorthConnect is awaiting feedback on the permitting applications. On the UK side, the Marine Licence and Planning permits are currently being processed. The period of public consultation is now complete and NorthConnect has received, and responded to, feedback from various stakeholders. Marine Scotland and Aberdeenshire Council are the permitting authorities involved in the assessment and decision making around each application. Aberdeenshire Council Committee is expected to determine the onshore planning application, which has received no formal objections, in Q1 2019 and following this, a Ministerial decision on the Marine Licences will be issued (also expected Q1 2019). NorthConnect was awarded IPA in January 2018 by Ofgem and has started the process to prepare for the FPA process, which will run throughout 2019. On the Norwegian part of the interconnector, the Foreign Trade License application was submitted in June 2017 and an up-dated version of the construction license application was submitted December 2017. The applications are currently being processed by the Norwegian Regulator, NVE. NVE has indicated that they will give a recommendation to the Norwegian Ministry of Petroleum and Energy (MOPE) during Q1-2019. Subsequent to NVE’s recommendation, MOPE will be responsible for finalising the application. NorthConnect expect that the processing of the application and the decision with conditions will be finalised during 2019. NorthConnect has initiated tendering the main contracts. The Invitation to Tender (ITT) for Cable System and Cable Installation and ITT for Converters were issued in Q3/Q4 2018. For the Cable System and Cable Installation, feedback on production capacity is expected at the end of Q4 2018, and the tenders for both Cable System and Converters are expected during Q1 2019. Until Q1 2019 NorthConnect will seek clarifications from the tenderers and prepare for the further processes on the main contracts. During 2019 the main contracts will be finalised. The Cable System and Cable Installation FEED studies and the Cable Lay analysis have been completed, and NorthConnect are currently preparing for negotiation of Crossing & Proximity Agreements with subsea asset owners and fish farms with the aim to have all agreements ready for signature by Q4 2019. Detailed slope stability studies within the Hardangerfjord have been conducted and validated the suitability of this route. The Converter FEED study has been finalised, and ongoing work includes getting the Peterhead connection details confirmed with Scottish & Southern Energy Networks, and Sima switchyard connection details confirmed with Statnett. In both UK and Norway there are ongoing communications with local stakeholders and landowners, ground investigations and design work to facilitate preparation for enabling works at the converter sites.
200 | CZ Northwest-South corridor | DE-CZ | https://tyndp.entsoe.eu/tyndp2018/projects/projects/200 | https://www.ceps.cz/cs/projekty-spolecneho-zajmu | Investment item no. 306 substation Vitkov: the construction phase is on progress, its finalization is expected by 2022 Investment item no. 309 OHL Vitkov - Prestice: the tendering process is on progress, its finalization is expected between 12/2018 - 02/2019 Investment item no. 308 OHL Vernerov - Vitkov: A new documentation for land and construction permit should be created in accordance with a new construction Act, its finalization and submission is expected by 2019 Investment item no. 312 substation Mirovka: the 1st construction phase is finalized. Documentaion preparation for the permit granting process for the second phase will start Investment item no. 314 OHL Mirovka - V413: the construction phase is on progress, its finalization is expected by 12/2019
210 | Wurmlach (AT) - Somplago (IT) interconnection | IT-AT | https://tyndp.entsoe.eu/tyndp2018/projects/projects/210 | corporate.enel.it/en/stories/a/2017/01/alpe-adria-energia | In October 2018, the Promoter met the Austrian Authorities (Federal Ministry for Sustainability and Tourism and Carinthia Region), in order to define the next steps to start the permitting procedure in Austria. At the same time, the Project Promoter is going to start the activities related to the submission of the Exemption request under the provision of the Reg. 714/2009.
214 | Interco Iceland-UK | IS-GB | https://tyndp.entsoe.eu/tyndp2018/projects/projects/214 | https://www.landsvirkjun.com/researchdevelopment/research/submarinecabletoeurope | A dialogue with the UK and Iceland government to ensure the political support necessary in order for the project to advance. This next phase of the project should then be based on recommendations from the UK-Iceland energy task force and includes cooperation between the two governments where the project's feasibility is assessed and the appropriate regulatory and financial support mechanisms are designed.
219 | EuroAsia Interconnector | GR-CY-IL | https://tyndp.entsoe.eu/tyndp2018/projects/projects/219 | www.euroasia-interconnector.com | Currently the Tender Documents for the construction of the Project are being finalised and will be made available to the pre-selected companies in order to prepare their bids. The procurement process follows the negotiated procedure with several rounds of negotiations which will lead to the award of the contracts. The expected date for the award of the contracts is indicative but is estimated to take place end of Q2 and beginning of Q3 2019.
230 | GerPol Power Bridge I | DE-PL | https://tyndp.entsoe.eu/tyndp2018/projects/projects/230 | http://www.liniakrajnikbaczyna.pl/ | Building permit for the investment No. 353 - Construction of new 400 kV double circuit line Krajnik – Baczyna.
235 | HVDC SuedLink Brunsbüttel/Wilster to Großgartach/Grafenrheinfeld | DE-DK/NO | https://tyndp.entsoe.eu/tyndp2018/projects/projects/235 | "http://suedlink.tennet.eu/home.html; https://www.transnetbw.de/de/uebertragungsnetz/dialog-netzbau/sued-link" | "Planned, but not yet in permitting The § 6 NABEG application documents for the Federal Sectoral Planning for each of the sections were submitted in 2017. The BNetzA held “application conferences” and defined the scopes of investigation for the sections. Since then the project promoters TransnetBW and TenneT are continually creating the application documents for the § 8 NABEG procedure. It is important to note that according to the TEN-E Regulation Article 10 (1), the project has not entered the status of “permitting” yet. Nonetheless, several activities with respect to planning and permitting (Federal Sectoral Planning) – which have to be conducted according to German Law before the permitting phase according to the TEN-E Regulation begins – have already been started and to some extent completed. Moreover a tender of major suppliers have been launched and contract awarding is planned for early 2020."
247 | AQUIND Interconnector | GB-FR | https://tyndp.entsoe.eu/tyndp2018/projects/projects/247 | www.aquindconsultation.co.uk; www.aquindconsultation.fr | Current stage: Permitting Ongoing activities: Completing Environmental Impact Assessments in France and the UK Preparing applications for the relevant permits and consents to the relevant authorities in France and the UK Preparation for a formal tender for converter stations and cables Approval of the project by the NRAs
254 | HVDC Ultranet Osterath to Philippsburg | DE | https://tyndp.entsoe.eu/tyndp2018/projects/projects/254 | https://www.transnetbw.de/de/ultranet https://www.amprion.net/Netzausbau/Aktuelle-Projekte/Ultranet/ | Planned, but not yet in permitting
260 | New Great Britain - Netherlands interconnection | NL-GB | https://tyndp.entsoe.eu/tyndp2018/projects/projects/260 | N/A | "Onshore grid connection feasibility phase: Agreement secured in 2017 for 1.5GW of coastal grid connection capacity in the UK (available from 2025) Grid connection in the Netherlands to be investigated in this phase"
270 | FR-ES project -Aragón-Atlantic Pyrenees | FR-ES | https://tyndp.entsoe.eu/tyndp2018/projects/projects/270 | https://www.ree.es/es/actividades/gestor-de-la-red-y-transportista/proyectos-de-interes-comun-europeos-pic; https://www.mincotur.gob.es/energia/planificacion/Planificacionelectricidadygas/desarrollo2015-2020/Paginas/desarrollo.aspx | Thorough CBA and feasibility analysis of Aragón-Atlantic Pyrenees and the related internal network reinforcement: Congestion studies on internal networks, detailed feasibility studies for Aragón-Atlantic Pyrenees and for the reinforcements needed on the internal grids, CBA assessment (2020)
276 | FR-ES project -Navarra-Landes | FR-ES | https://tyndp.entsoe.eu/tyndp2018/projects/projects/276 | https://www.ree.es/es/actividades/gestor-de-la-red-y-transportista/proyectos-de-interes-comun-europeos-pic; https://www.mincotur.gob.es/energia/planificacion/Planificacionelectricidadygas/desarrollo2015-2020/Paginas/desarrollo.aspx | Thorough CBA and feasibility analysis of Navarra – Landes and the related internal network reinforcement: Congestion studies on internal networks, detailed feasibility studies for Navarra – Landes and for the reinforcements needed on the internal grids, CBA assessment (2020)
284 | LEG1 | LY-GR | https://tyndp.entsoe.eu/tyndp2018/projects/projects/284 | www.greenpower2020.net | LEG1 is currently planned but not permitting. We aim at finalising the high-level feasibility study description in the coming weeks, then identify activities which will require permits (subsea surveys, etc) and apply for the said permits. LEG1 have obtained outstanding supply chain support and involvement!
285 | GridLink | GB-FR | https://tyndp.entsoe.eu/tyndp2018/projects/projects/285 | www.gridlinkinterconnector.com | Current phase is Advanced Feasibility - expected to finish in December 2018 Next phase is Full Development - expected to finish in March 2021
286 | Greenlink | IE-GB | https://tyndp.entsoe.eu/tyndp2018/projects/projects/286 | https://www.greenlinkinterconnector.eu/ | The current activities being carried out by the PCI are: o Conducting subsea surveys along the cable route for the PCI, commenced in September 2018 and expected to be completed in January 2019. o Conducting onshore environmental and technical surveys on the onshore cable route and converter station sites in Ireland and Wales, expected to be completed in February 2019 o Liaising with landowners on the Irish and Welsh cable route and the potential Welsh converter station sites for the acquisition of land rights required for construction and operation of the interconnector. o Undertaking an Official Journal of the European Union (OJEU) compliant procurement process for the engineering, procurement and construction of the interconnector, including the HVDC converter stations and cables. Greenlink is currently concluding the pre-qualification questionnaire stage and expects to commence the stage 1 invitation to tender by the end of November 2018. o Liaising with EirGrid in relation to an Irish grid connection offer, expected to be issued by EirGrid by the end of December 2018. The next stage of the PCI, facilitated by the activities above, is the submission of planning (in the UK and Ireland “planning” in this context means permitting) applications in Ireland and Wales, expected to be submitted by the end of April 2019.
293 | Southern Aegean Interconnector |  | https://tyndp.entsoe.eu/tyndp2018/projects/projects/293 | http://eunice-group.com/projects/aegean-project | During next year (2019) the relative Approval of the Environmental Impact's Assessment of the whole project is expected to be issued, as well as the Final Connection Terms by the Greek System Operator.
296 | Britib | FR-GB | https://tyndp.entsoe.eu/tyndp2018/projects/projects/296 | www.grupocobra.com | Inclusion in PCI list.
297 | BRABO II + III | NL-BE | https://tyndp.entsoe.eu/tyndp2018/projects/projects/297 | http://www.elia.be/en/projects/grid-projects/brabo | Brabo II: Construction works for the 380kV line connection between substation Lillo and Liefkenshoek is ongoing. The installation of the 380 kV GIS at Lillo is almost finished. The construction works of 380kV line connection between Lillo and Zandvliet is going to start after the demolition of the 150kV line connection (Planned beginning of 2019). The complete 380kV line connection between Liefkenshoek – Lillo – Zandvliet is planned to be commissioned end of 2020 Brabo III: Next and final phase is the construction of the 380kV line connection between Liefkenshoek and Mercator. Commissioning is planned in 2025.
299 | SACOI3 | ITsar-Itcn | https://tyndp.entsoe.eu/tyndp2018/projects/projects/299 | https://www.terna.it/en-gb/sistemaelettrico/pianodisviluppodellarete/progettidiinteressecomune.aspx | currently the permitting procedure is ongoing, it is expected to last till end 2021
309 | NeuConnect | GB-DE | https://tyndp.entsoe.eu/tyndp2018/projects/projects/309 | www.neuconnect.eu | Currently, NeuConnect is working towards the launch of the EPC procurement process. The activities underway to enable this milestone to occur include: 1 – Delivery of final Seabed Survey reports to allow the subsea route and cable design to be issued to the bidders. 2 – Delivery of The Functional Specification of the Interconnector component parts including HVDC Subsea Cables and Converter Station to issue to potential bidders. 3 – Drafting of the EPC Procurement Contracts.
312 | St. Peter - Tauern (AT internal) | DE-AT | https://tyndp.entsoe.eu/tyndp2018/projects/projects/312 | http://www.apg.at/de/netz/netzausbau/PCI/StPeterTauern | Approval expected until the End of 2018. Start of construction works beginning of 2019. Commissioning in 2023 | Dieses Projekt ist durch den beabsichtigten Lückenschluss ein Element besonderer Wichtigkeit im österreichischen 380-kV-Ring zwischen den Netzknoten St. Peter und Tauern. In den Leitungszug werden Umspannwerke für die Anspeisung der regionalen 110-kV-Verteilernetze integriert. Dadurch wird die für die Wirtschaft so wichtige Versorgungssicherheit in den Verteilernetzen der Bundesländer Oberösterreich und Salzburg erheblich verbessert. Darüber hinaus werden die im Süd-Westen gelegenen Speicherkraftwerke mit österreichischen und europäischen Windenergiestandorten sowie den Verbraucherzentren verbunden. Ohne die Salzburgleitung können keine weiteren Pumpspeicherpotenziale erschlossen sowie die Netzintegration der Windkraft in Österreich nicht im erforderlichen Ausmaß bewerkstelligt werden.
313 | Isar/Altheim/Ottenhofen (DE) - St.Peter (AT) | DE-AT | https://tyndp.entsoe.eu/tyndp2018/projects/projects/313 | http://www.apg.at/de/netz/netzausbau/PCI; http://www.netzentwicklungsplan.de/en | "Permit Granting Process (acourding to ACER PCI Monitoring questionnaire submitted on 31 March 2018) with the following main works and activities: - Environmental and spatial studies - Identification of alternative solutions / site identification - Public consultations - Preparation of permitting files, contracts and other documents - Detailed technical design" | Das Projekt ist als sehr wichtig einzustufen, weil es einen besseren Stromaustusch durch flexible, marktorientierte Interaktion erlaubt. Z.B. von den österreichischen Pumpspeicherkraftwerken mit Windenergieanlagen nördlichen Regionen Europas sowie von Einspeisern erneuerbarer Energie und Kunden in verschiedenen Ländern. Mit der 380-kV-Deutschlandleitung entstehen überdies erhöhte Austauschleistungen zwischen Österreich und Deutschland, was ein wichtiger Beitrag zur Versorgungssicherheit aber vor allem für den europäischen Energiebinnenmarkt ist. Für die Wirtschaft ist wichtig, dass die Versorgungs- und Systemsicherheit garantiert wird.
320 | Slovenia-Hungary/Croatia interconnection | SI-HU | https://tyndp.entsoe.eu/tyndp2018/projects/projects/320 | https://www.cirkovce-pince.eu/ | For the substation Cirkovce, tendering process is undergoing and will be completed by April 2019. Afterwards, construction of the substation will begin. For the OHL Cirkovce-Pince, a request for building permit was submitted to the competent authority on 14th May 2018. Construction works are expected to start from 30th Septembre 2019, thus, this being final date of permit granting process.
323 | Dekani (SI) - Zaule (IT) interconnection | SI-IT | https://tyndp.entsoe.eu/tyndp2018/projects/projects/323 | 0 | Ongoing activities for final building permits in Slovenia
324 | Redipuglia (IT) - Vrtojba (SI) interconnection | SI-IT | https://tyndp.entsoe.eu/tyndp2018/projects/projects/324 | 0 | Ongoing activities to obtain all the building permits in Slovenia.
325 | AT, SI, IT - South-East Alps Project | AT-IT | https://tyndp.entsoe.eu/tyndp2018/projects/projects/325 | http://www.apg.at/de/netz/netzausbau/PCI/LienzObersielach | feasibility study | Freier Warenverkehr ist ein Herzstück der Europäischen Union. Das gilt auch für Energie in jeder Form – im Energiebinnenmarkt muss Energie - im besonderen Strom - ungehindert über die nationalen Grenzen fließen können. Im größeren Markt ist Elektrzität á la longue billiger ist als im eng segmentierten Markt. Besser vernetzte Märkte bzw gemeinsame Preiszone bieten auch höhere Versorgungssicherheit. Der Ausbau grenzüberschreitender Netzinfrastruktur und die Verbindung der Marktgebiete ist somit von essentieller Bedeutung. Wir unterstützen deshalb die Durchführung der Machbarkeitsstudie zur Verstärkung der Leitung Westtirol – Zell/Ziller.
330 | 4th 400kV CZ-SK interconnector | SK-CZ | https://tyndp.entsoe.eu/tyndp2018/projects/projects/330 | On the Czech side: https://www.ceps.cz/cs/rozvoj-ps; On the Slovak side: https://www.sepsas.sk/ProgramRozvoja.asp?kod=338 | On the Czech side, launching of the Environment Impact Assessment process and settlement of the regional land use development principles and local land use plans is foreseen. On the Slovakia side; currently there is no running activities within SEPS related directly to this project. The next step is Final Investment Decision for building the substation Ladce that is expected to be granted in the first half of the year 2020.
335 | North Sea Wind Power Hub | DK/NL-DE | https://tyndp.entsoe.eu/tyndp2018/projects/projects/335 | https://northseawindpowerhub.eu/ | Assess phase – Based on the identified opportunity: An internationally coordinated, large scale far offshore wind energy from the North Sea to deliver energy at competitive prices around 2030 and facilitate meeting the Paris agreement. The project is committed to explore and develop regional socio-economic beneficial and reliable offshore infrastructure, including possible conversion into P2G, that supports wind farm operations and interconnections between markets. In the current assess phase the project is explores the different options to deliver on this opportunity, through detailed techno-economic feasibility studies and consultation of stakeholders.
349 | MAREX Organic Power Interconnector | UK-IE | https://tyndp.entsoe.eu/tyndp2018/projects/projects/349 | www.organicpowerinternational.com | PCI Status in 2019 Grid connection to be secured from EIRRID in 2019 Transmission wayleaves to be secured in 2019

## storage projects
TYNDP project number | Name of the project | Country/ies | TYNDP detailed project sheet [including project description and outcomes of the Cost Benefit Analysis] | Project website (as set by the promoter) | Current phase of the project [information as submitted by the promoter for the PCI process] | In your opinion, is a proposed project significantly contributing to market integration/sustainability/security of supply/competition and therefore needed from an EU energy policy perspective?
1001 | Kaunertal Extension Project | AT | https://tyndp.entsoe.eu/tyndp2018/projects/storage_projects/1001 | https://www.tiwag.at/en/about-tiwag/power-stations/expansion-of-hydropower/our-power-station-projects/the-kaunertal-expansion-project/ | In Permitting; Environmental Impact Assessment | Es ist absolut essenziell, dass der Ausbau des Kraftwerks Kaunertal weiterhin auf der Liste der „Infrastrukturprojekte von gemeinsamem Interesse der EU (PCI)“ bleibt. Das Projekt: Konkret ist der Bau einer Oberstufe im Platzertal (Gemeinde Pfunds) sowie eines Pumpspeicherkraftwerks im Kaunertal geplant. Zusätzliches Wasser soll von der Gurgler und Venter Ache in den Gepatsch-Stausee abgeleitet werden. Neben den bereits fertig gestellten Druckschacht Kaunertal wird auch ein zusätzliches Kraftwerk in Prutz errichtet. Insgesamt würden hierfür rund € 1,3 Milliarden investiert! Folgenden Mehrwert bringt das Projekt mit sich: 1. Als Pumpspeicherkraftwerk wird der Ausbau des Kraftwerks Kaunertal einen wesentlichen Beitrag zur europäischen Energiesicherheit und dem Klimaschutz liefern: Sonnen- und Windenergie unterliegen starken Schwankungen; das Kraftwerk Kaunertal wird die hierfür erforderliche Regel- und Ausgleichsenergie zur Verfügung stellen. Mit dem zusätzlichen Speicher Platzertal, dem Speicher Versetz und dem zweiten Kraftwerk in Prutz und Imst kann die Gesamterzeugung der beiden bestehenden Kraftwerke deutlich gesteigert werden. Durch den Ausbau können jährlich rund 790 Millionen kWh an nachhaltig erzeugter elektrische Energie geliefert werden. Zum Vergleich: Für die Erzeugung der gleichen Strommenge in einem Kohlekraftwerk müssten ca. 250.000 t Kohle verfeuert werden. Daher ist dieses Projekt auch ein wesentlicher Beitrag zum Klimaschutz! 2. Die in der österreichischen Energiestrategie #mission2050 vorgesehene Umstellung der heimischen Stromproduktion auf 100 Prozent Erneuerbare bis 2030 erfordert systemdynamische Anpassungen. Gefordert sind flexible Kapazitäten zur Spannungsstabilisierung, Schwarzstartfähigkeit und Inselbetrieb auf Ebene des Übertragungssystems. Wie in den Alpenregionen üblich, erfüllt das Projekt Kaunertal durch einen erheblichen natürlichen Zufluss alle diese Systemanforderungen in besonderer Weise. Zusätzlich trägt das Projekt wesentlich zur Gewährleistung der Versorgungssicherheit bei. Auch das Land Tirol selbst verfolgt mit seiner „Energiestrategie 2050“ die Zielsetzung einer (bilanziellen) Energieautonomie: Um diese Zielsetzung bis zum Jahr 2050 zu erreichen, ist es erforderlich das vorhandene Wasserkraftpotenzial (rund 30.000 TJ) auszuschöpfen. 3. Nachhaltigkeit: Ein im Herbst 2016 duchgeführtes Gutachten des Internationalen Wasserkraftwerksverbandes (IHA) hat 21 Themenbereiche analysiert: In acht Bereichen erhielt das Projekt Kaunertal die besten Noten; zehnmal wurde die „grundlegend gute Praxis" erreicht. Nur in drei Themenfeldern blieb man unter dem Duchschnitt. Insgesamt wurde dem Projekt auch aus Nachhaltigkeitsgesichtspunkten ein gutes Zeugnis ausgestellt.
1002 | iLand | BE | https://tyndp.entsoe.eu/tyndp2018/projects/storage_projects/1002 | https://www.iland-energystorage.com | Due to its multi-functional nature, iLand is progressing on several fronts at the same time: • Following the establishment of a roadmap in 2018, concrete projects are being identified and are starting to be implemented with regards to the aquaculture aspects of iLand. iLand is working in cooperation with the University of Gent on this aspect of the project. • The feasibility study subsidized by the Belgian Energy Transition Fund was launched in October 2018 and its completion is expected by early 2020. • iLand plans to apply for CEF funding in one or more of the 2019 calls. • Consultations are pending to enhance iLand’s contribution to the environment, including finding solutions to mitigate the plastic pollution of the seas and oceans. • The Federal Belgian Government (Secretary of State of the North Sea) is designing a new Maritime Spatial Plan for the 2020-2026 period. The planning began in 2017 and iLand’s promoters have been heavily involved in the process through multiple interactions with the government. The final design is expected by mid 2019. The value 01/01/1900 is provided below exclusively to comply with the default format requirement, which is inappropriate for a project that is moving ahead on several fronts at the same time.
1003 | Hydro-pumped storage in Bulgaria - Yadenitsa | BG | https://tyndp.entsoe.eu/tyndp2018/projects/storage_projects/1003 | www.nek.bg/yadenitsa | After completing the procedure for approving the Detailed Site Development Plan NEK EAD will obtain water usage permission and will submit documents for issuing Construction Permit. Final milestone to be achieved: issued Construction Permit
1004 | Estonian PHES (pumped-hydro energy storage) | EE | https://tyndp.entsoe.eu/tyndp2018/projects/storage_projects/1004 | www.energiasalv.ee | Area Planning Approval
1006 | HPS AMFILOCHIA | GR | https://tyndp.entsoe.eu/tyndp2018/projects/storage_projects/1006 | hps-Amfilochia.gr | The Hellenic Power Transmission Operator (HPTO) has suggested a minor modification, concerning the interconnection between the reversible Units in the Powerhouse and the Ultra High Voltage Center. This change requires the update of the Environmental Study in that point. The HPTO issued the interconnection terms for the Project in July 2018. The remaining issues are related with all the provisions for land occupancy and constitute the prerequisites for the issuance of construction permit and the beginning of construction.
1009 | Kruonis pumped storage power plant extension project | LT | https://tyndp.entsoe.eu/tyndp2018/projects/storage_projects/1009 | http://www.gamyba.le.lt/en/activities/projects/kruonis-pumped-storage-power-plant-expansion | Currently two feasibility studies are being implemented: 1) Evaluation of the technical condition of the infrastructure and penstock site of the Kruonis HPSPP (deadline 15 March 2019); 2) Evaluation of suitability of different technological solutions for the extension of Kruonis HPSPP and the socioeconomic analysis of the Project (deadline 25 October 2019). It is estimated to complete both studies on time.
1011 | "REVERSIBLE PUMPED-STORAGE HYDROELECTRIC EXPLOITATION ""MONT- NEGRE"" POWER 3,300 MW ZARAGOZA, SPAIN" | ES | https://tyndp.entsoe.eu/tyndp2018/projects/storage_projects/1011 | www.ingenieriapontificia.com | Waiting for the evaluation of the Environmental Impact Project Report
1012 | Purifying -Pumped Hydroelectric Energy Storage (P-PHES Navaleo) | ES | https://tyndp.entsoe.eu/tyndp2018/projects/storage_projects/1012 | 0 | Permiting a Modified Enviromental Project including a Power Line to SET Montearenas - June 2019
1013 | CAES Zuidwending, NL | NL | https://tyndp.entsoe.eu/tyndp2018/projects/storage_projects/1013 | http://www.correnergystorage.com/ | Project development Phase 2. This includes Project Commercialisation Phase 2, EIA and Permitting and Engineering Design of the CAES facility.
1014 | Coire Glas | UK | https://tyndp.entsoe.eu/tyndp2018/projects/storage_projects/1014 | http://sse.com/whatwedo/ourprojectsandassets/renewables/CoireGlas/ | Waiting for formal approval for this revised application is expected from the Scottish Government in April 2019. Project scheduled to move into detailed refinement phase in March 2020
1015 | Cruachan II | UK | https://tyndp.entsoe.eu/tyndp2018/projects/storage_projects/1015 | https://www.scottishpowergeneration.com/our-projects/cruachan-2 | 2 year Ornithology surveys to be completed by year end Technical assessments to identify options for increasing the storage capacity of upper reservoir underway and to complete in November 2018. Camera trap surveys for wildcat and pine marten to be completed by year end.
1019 | TWO REVERSIBLE HIDROELECTRIC PLANTS: GIRONES & RAIMATS IN SPAIN | ES | https://tyndp.entsoe.eu/tyndp2018/projects/storage_projects/1019 | info not submitted | The project is currently focused on the permit granting process. The environmental Impact Assessment procedure was initiated in July 2017 regarding the environmental authorisation. The scoping report was received in March 2018 after requiring by the promoter a scoping opinion to relevant stakeholders. Currently environmental impact studies are at the beginning. With respect to the water concession, water administrative file i officially "still being processed" despite the concession request was made in 2012. In addition, the technical services of the General Directorate of Water have indicated it is not possible to analyse circumstances of our file (e.g. we are PCI) until a previously initiated administrative file has been resolved. The General Directorate of Water cannot answer us when the resolution of the water concession will be, despite the fact that we haver repeatedly asked.
1022 | CARES (Compressed Air Renewable Energy Storage) | UK | https://tyndp.entsoe.eu/tyndp2018/projects/storage_projects/1022 | www.cares-pci.uk | Competitive tenders and supplier selection for: - Planning and environmental - TES design - Geotechnical - Public Relations Validation of revenue streams by a third party Continue filling the vacancies, though with the step of engaging them deferred until we have the funding (this delay is likely to result in some no longer being available when the time comes, but doing this work now will reduce the start-of-funded-project workload and speed the organisational ramp-up) Finalise and sign a lease agreement with the land / geological rights owner If we receive sufficient funding that has an appetite for grant risk, we will start, ahead of approval of the CEF grant, some or all of the following critical path activities: - TES design - Sufficient engineering for grid connection studies - Grid connection studies - Season-determined habitat and wildlife surveys - European roll-out study activities - Continuing to seek funding - Geotechnical work on the smaller plant - Recruitment to do the above
1023 | Cheshire Gas CAES | UK | https://tyndp.entsoe.eu/tyndp2018/projects/storage_projects/1023 | To be set up when PCI status is granted | Continue to seek funding to enable development work on this project
1025 | Silvermines Hydroelectric Power Station | IE | https://tyndp.entsoe.eu/tyndp2018/projects/storage_projects/1025 | silvermineshydro.com/ | Water Monitoring & Analysis (lower reservoir) - Baseline survey within the open-pit water body, at the pit wall, in the stream above and below the pit level and at the Knight Shaft (or its outfall). To include the analysis and measurement of the following parameters; Real-time water level sensors and suspended sediment load; Near, mid and far field chemical and physical water sampling throughout the study period; Moored optical sensors for long term turbidity measurements at multiple locations; VIPS near real-time in situ trace element monitoring and profiling; meteorological station installed for the duration of the study period. Geotechnical Analysis & Monitoring (lower reservoir) - Materials recovered by the underwater sampling vehicle to be selectively sampled and analysed based on material/rock type for the geotechnical parameters to include PSD analysis, Resistance to Fragmentation, LAA tests, water absorption, MSS tests, etc. Samples will undergo geological, chemical and petrographic testing. A geological examination of the samples is to be carried out to identify the presence or absence of calcareous mudstone / siltstone lithologies. The purpose of these tests will be to evaluate the chemical characteristics of the material and provide information in relation to the nature of the material.
1026 | Hydro pumped storage Riedl | DE | https://tyndp.entsoe.eu/tyndp2018/projects/storage_projects/1026 | https://www.verbund.com/en-at/about-verbund/power-plants/energiespeicher-riedl | permission phase
1027 | P-PHES CUA | ES | https://tyndp.entsoe.eu/tyndp2018/projects/storage_projects/1027 | info not submitted | Permiting the Declaration Environmental - December 2019
1029 | PSPP Kozjak | SL | https://tyndp.entsoe.eu/tyndp2018/projects/storage_projects/1029 | http://www.dem.si/sl-si/Razvojne-možnosti/ČHE-Kozjak | Current phase of the project is the second phase of the EIA assessment in accordance with Slovenian regulations
1030 | MAREX Organic Power Energy Storage | ES | https://tyndp.entsoe.eu/tyndp2018/projects/storage_projects/1030 | www.organicpowerinternational.com | PCI status